ZGHAPARI

ზღაპარი

Multi-Agent Development Plan

Turn Your Child Into the Hero of Their Own Georgian Fairy Tale — In Minutes. Spec-Driven Development · Claude Code Multi-Agent Pipeline · Human-in-the-Loop

Version 1.0  ·  March 2026

# 1. Executive Summary

Zghapari is a web platform that lets parents create personalized, AI-illustrated children's storybooks rooted in Georgian culture and language. This document defines the complete development approach — from the AI tooling and agent architecture to the milestone breakdown and daily workflow.

Two developers collaborate on a shared GitHub monorepo. Development is managed through a Spec-Driven, Multi-Agent pipeline built on top of Claude Code. Every phase of the SDLC has a dedicated AI agent. Nothing moves forward without explicit human approval.

Core principle: Specifications are written and approved before any code is written.

The biggest technical risk is character consistency across illustrations — this must be validated first.

Image generation: Nano Banana Pro (Google Gemini 3 Pro Image) — supports character consistency across 14 reference images.

Tech stack: React + TypeScript (frontend), Node.js + TypeScript + NestJS (backend).

# 2. The Approach: Spec-Driven + Multi-Agent

Traditional development starts with code. This project starts with specifications. Every feature goes through a structured pipeline before a single line of application code is written.

### 2.1 Why Spec-Driven Development

- Specifications become the source of truth — agents read them, not vague prompts.

- Every agent knows exactly what to build before it starts.

- You review and approve at every phase — nothing is automated away from you.

- Mistakes are caught in specs (cheap) not in code (expensive).

### 2.2 Why Multi-Agent

- Each agent has a single, focused responsibility — no agent tries to do everything.

- Agents that can run in parallel (frontend, backend, AI pipeline) do so simultaneously.

- Context stays clean — each agent only sees what it needs to.

- You stay in control — agents are called manually, one at a time.

### 2.3 The Full SDLC Pipeline

Phase 0 — Research (before anything else) Research agent → Georgian LLM evaluation, character consistency spike, payment provider research, legal/compliance summary You review findings → approve before Phase 1 Phase 1 — Discovery BA agent → constitution.md (project principles) BA agent → spec.md (user stories, acceptance criteria) BA agent → clarify (structured questions to fill gaps) You approve spec → proceed to Phase 2 Phase 2 — Planning Architect agent → plan.md, data-model.md, api-spec.md You approve architecture → proceed to Phase 3 Phase 3 — Build (parallel) Frontend Engineer + Backend Engineer + AI Pipeline Engineer + Integrations Engineer run simultaneously You review code in VS Code → proceed to Phase 4 Phase 4 — Quality (parallel) Code Reviewer + Tester run simultaneously Fix loop back to engineers if issues found You approve → proceed to Phase 5 Phase 5 — Ship DevOps agent → creates PR with full description You review PR on GitHub → merge

Human checkpoint: Nothing moves from one phase to the next without your explicit "approved, proceed" message.

This is intentional. Automate later once you understand the patterns.

# 3. The Agent Team

10 specialized agents, each defined as a simple text file in .claude/agents/. They have no cost when idle — they only activate when you call them.

| Agent | Phase | Responsibility | Outputs |
| --- | --- | --- | --- |
| Orchestrator | All phases | Reads your request, delegates to all agents, synthesizes results | Task list, status updates |
| Research | Phase 0 | Investigates AI models, payments, legal requirements | Research reports in .specify/research/ |
| BA | Phase 1 | Writes user stories, acceptance criteria, edge cases | spec.md |
| Architect | Phase 2 | System design, data model, API contracts, AI pipeline design | plan.md, data-model.md, api-spec.md |
| Frontend Engineer | Phase 3 | React components, pages, i18n, Georgian script rendering | Code in /frontend |
| Backend Engineer | Phase 3 | Node.js API, DB, auth, async jobs, multilingual data model | Code in /backend |
| AI Pipeline Engineer | Phase 3 | Image generation, character consistency, job queues, progress API | Code in /backend/ai-pipeline |
| Integrations Engineer | Phase 3 | Georgian payments, PDF generation, content moderation middleware | Code in /backend/integrations |
| Code Reviewer | Phase 4 | Reviews code for logic, security, privacy, Georgian font handling | Review report (read-only) |
| Tester / QA | Phase 4 | Unit tests, E2E tests, privacy/safety checklist | Test files, bug report |
| DevOps | Phase 5 | Git branch, CI/CD, PR description, deployment config | PR on GitHub |

# 4. Skills — The Workflow Engine

Skills are reusable workflow files stored in .claude/skills/. Each skill tells Claude exactly how to behave for a specific phase of the SDLC. You invoke them manually by typing a simple phrase. Think of them as your SDLC playbook — one skill per phase, each one self-contained.

### 4.1 How a skill works

A skill file (SKILL.md) contains: the goal of this phase, which agent(s) to invoke, what inputs to read, what outputs to produce, the exact steps to follow, and how to present results for your review.

Example — when you type "use specify skill — user authentication":

- Claude reads .claude/skills/specify/SKILL.md

- Activates the BA agent with the right context

- BA agent reads the constitution.md and product description

- Interviews you with targeted questions about the feature

- Writes a structured spec.md in .specify/specs/NNN-auth/

- Presents it to you for review before anything else happens

| Skill | You type | Agent(s) involved | Output |
| --- | --- | --- | --- |
| constitution | use constitution skill | BA | .specify/memory/constitution.md |
| specify | use specify skill — [idea] | BA | .specify/specs/NNN/spec.md |
| clarify | use clarify skill | BA | Clarification section added to spec.md |
| plan | use plan skill — [tech constraints] | Architect | plan.md, data-model.md, api-spec.md |
| tasks | use tasks skill | Orchestrator | tasks.md with parallel markers |
| implement | use implement skill | Frontend, Backend, AI Pipeline, Integrations | Code committed to feature branch |
| review | use review skill | Code Reviewer + Tester | Review report + test files |
| ship | use ship skill | DevOps | PR created on GitHub |

### 4.2 The specify skill in detail (most important one)

This is the entry point for every new feature. It follows the spec-kit pattern — focus on what and why, not how.

You type: use specify skill — a user authentication system with Google login and email/password What happens: 1. BA agent reads constitution.md and product description 2. Asks you up to 5 clarifying questions 3. You answer 4. BA writes .specify/specs/001-auth/spec.md containing: - Feature overview - User stories (As a parent, I want to...) - Acceptance criteria for each story - Edge cases and error states - Out of scope (explicitly listed) - Open questions (if any remain) 5. You read it and say "approved" or "change X"

# 5. Project Structure

Everything lives in the zgapari monorepo on GitHub. Here is the complete folder structure and what each part does.

| Path | Purpose |
| --- | --- |
| CLAUDE.md | Project brain — loaded in every Claude Code session |
| frontend/ | React app — all UI, components, pages, i18n |
| backend/ | Node.js API, DB, auth, async jobs |
| .specify/memory/constitution.md | Governing principles — every agent reads this first |
| .specify/specs/NNN-feature/spec.md | User stories & acceptance criteria per feature |
| .specify/specs/NNN-feature/plan.md | Technical architecture and decisions |
| .specify/specs/NNN-feature/tasks.md | Ordered task list with parallel markers |
| .specify/specs/NNN-feature/data-model.md | DB schema and entity relationships |
| .specify/specs/NNN-feature/contracts/api-spec.md | API contracts between frontend and backend |
| .specify/research/ | AI feasibility, payment, legal research reports |
| .claude/agents/*.md | One file per agent — their role, tools, and constraints |
| .claude/skills/*/SKILL.md | Workflow files — one per phase of the SDLC |

# 6. Technology Decisions

| Area | Decision | Rationale |
| --- | --- | --- |
| Frontend | React + TypeScript | Type safety critical for a project this size; Georgian script and i18n easier to manage |
| Backend | Node.js + TypeScript + NestJS | Structure, decorators, and built-in DI make async job handling cleaner |
| Database | PostgreSQL | Relational — important for user/child/book/page relationships and character refs |
| Job Queue | BullMQ + Redis | Async image generation jobs; progress reporting; retry logic built in |
| Image Generation | Nano Banana Pro (Gemini 3 Pro Image) | Character consistency across 14 inputs; 4K output; multilingual text rendering in images |
| Text Generation | To be decided in M0 spike | Evaluate GPT-4o, Claude, Gemini specifically for Georgian language quality |
| File Storage | S3-compatible (AWS or GCS) | Images, PDFs, character references — CDN-served to end users |
| PDF Generation | Puppeteer (server-side) | Georgian font embedding, 300 DPI, CMYK-safe color space |
| Auth | JWT + Google OAuth | Email/password + social login as per product spec |
| Payments | BOG iPay or TBC Pay | Stripe has limited support in Georgia — validate in M0 research |
| CI/CD | GitHub Actions | Already using GitHub; straightforward pipeline for lint, test, build, deploy |
| Deployment | To be decided in M0 | Cloud provider (AWS/GCP/Vercel) based on Georgian data residency needs |

### 6.1 Note on Nano Banana Pro

Nano Banana Pro is Google's Gemini 3 Pro Image model — the image generation API you selected. Key facts relevant to Zghapari:

- Supports character consistency across up to 14 input images — directly addresses the hardest technical challenge.

- Up to 5-person identity preservation in complex scenes.

- 4K output resolution — important for print-quality PDFs.

- Advanced multilingual text rendering — useful for Georgian text in images.

- Available via Google AI API directly or via providers like Together AI and PiAPI.

Still validate in M0: Nano Banana Pro's character consistency must be prototyped with actual children's photos and the Pirosmani/modern art styles before committing to it as the production solution.

Midjourney remains a backup option but has no official API — access is via unofficial wrappers only.

# 7. Critical Risks & How We Address Them

### 7.1 Character consistency [CRITICAL]

The same child character must look recognizably identical across all pages of a book and across multiple books. This is the product's core promise.

- Mitigation: M0 feasibility spike — prototype before any other development begins.

- Approach: Nano Banana Pro's multi-reference image input + stored character reference per child profile.

- Fallback: IP-Adapter or InstantID if Nano Banana Pro proves insufficient.

- Definition of success for M0: Character is visually consistent across 8 generated illustrations.

### 7.2 Georgian language quality

LLMs vary significantly in Georgian text output quality. Poor quality would undermine the product's cultural promise.

- Mitigation: M0 LLM evaluation — test GPT-4o, Claude, Gemini specifically for Georgian story generation.

- Score on: grammar, vocabulary richness, age-appropriateness, cultural accuracy.

- Document the winner and use it exclusively for story text generation.

### 7.3 Children's photo privacy [CRITICAL]

Photos of children are sensitive data. Any breach or misuse would be fatal to the product.

- Original photos are processed to generate character references, then offered for deletion.

- Only the character reference (not the raw photo) is stored long-term.

- Character references are encrypted at rest and isolated from other data stores.

- Clear plain-language privacy policy written before any user testing.

- Tester agent has an explicit privacy checklist that runs on every build.

### 7.4 Payment integration in Georgia

Stripe has limited support for Georgian businesses. Wrong choice here causes launch delays.

- Mitigation: M0 payment research — test BOG iPay and TBC Pay APIs, sandbox availability, fees.

- Architecture: payment provider is abstracted behind an interface — swapping providers is a config change, not a rewrite.

### 7.5 Georgian script in PDFs

PDF generation must render Georgian (Mkhedruli) script correctly with proper font embedding.

- Use Puppeteer server-side with explicitly embedded Georgian fonts.

- Test early — this is a common failure point that is expensive to fix late.

- Tester agent has a specific Georgian rendering test in its checklist.

# 8. Development Milestones

| Milestone | What's included | Est. duration | Owner |
| --- | --- | --- | --- |
| M0: Research | AI feasibility spike (character consistency, Georgian LLMs, art styles), payment provider research, legal/compliance summary | 1–2 weeks | Both |
| M1: Foundation | Auth, user accounts, child profiles, DB, basic UI shell, project infrastructure | 2–3 weeks | Both |
| M2: Story Engine | Text generation, story creation wizard, basic editor, template system | 2–3 weeks | Both |
| M3: Illustration Pipeline | Image generation via Nano Banana Pro, character consistency, async job queue | 3–4 weeks | Backend / AI |
| M4: Photo-to-Character | Photo upload, character generation, profile storage, style variants | 2 weeks | Backend / AI |
| M5: Reader & Export | On-device reader, PDF generation with Georgian fonts, library/bookshelf | 2 weeks | Frontend |
| M6: Payments | Free tier tracking, BOG/TBC Pay integration, watermarking, per-page pricing | 1–2 weeks | Backend |
| M7: Polish & Launch | Content moderation, i18n, performance tuning, WCAG 2.1 AA, final QA | 2–3 weeks | Both |

Total estimated duration: 17–23 weeks from project setup to launch-ready MVP.

M0 (Research) is the gating milestone — no M1 development begins until M0 findings are reviewed and approved.

M3 (Illustration Pipeline) is the longest and most technically risky milestone.

# 9. The Daily Workflow

This is how you and your partner work with the agent pipeline day-to-day.

### 9.1 Starting a new feature

Day 1 You: "use specify skill — [describe the feature]" BA agent → writes spec.md You read it → "approved" or "change X" You: "use clarify skill" BA agent → asks targeted questions, updates spec.md You answer → "approved, proceed to planning" Day 2 You: "use plan skill — [any tech constraints]" Architect → writes plan.md, data-model.md, api-spec.md You read it → "approved" You: "use tasks skill" Orchestrator → writes tasks.md with ordered tasks and [P] parallel markers You review → "looks good, proceed" Day 3–N You: "use implement skill" Engineers work in parallel on their areas You review code in VS Code → "looks good" Final day You: "use review skill" Code Reviewer + Tester run → report + tests Fix anything flagged You: "use ship skill" DevOps → PR created You → review and merge on GitHub

### 9.2 Developer ownership

Work is split by domain, not by file. Both developers have full visibility into the whole codebase.

- Soso: Frontend — React app, UI components, pages, i18n, Georgian script rendering, mobile-first design.

- Partner: Backend — Node.js API, database, auth, job queues, AI pipeline, integrations, payments.

- Shared: Architecture decisions, code review of each other's PRs, M0 research.

### 9.3 Branching strategy

- main — stable, working code only. Never commit directly here.

- feature/NNN-feature-name — one branch per feature, named after the spec folder.

- Both developers pull from main at the start of each feature.

- PRs are reviewed by the other developer before merging.

# 10. Setup Steps (In Order)

What needs to be built before development can start:

- Repo on GitHub — ✅ Done (zgapari)

- CLAUDE.md skeleton — ✅ Done

- All 10 agent files in .claude/agents/ — ← In progress

- All 8 skill files in .claude/skills/ — Next

- .specify/ folder — constitution + templates — After skills

- M0: Run Research agent — AI feasibility spike — First real work

- Run BA + Architect agents — constitution + spec + architecture — After M0

- Build milestone by milestone — When setup and design are done

# 11. Deliberately Out of Scope — For Now

These will be introduced once the pipeline is working and you understand the patterns:

- Automated hooks — no auto-triggers on file save, commit, or agent stop. Everything is called manually.

- CI/CD automation — GitHub Actions pipeline is set up in M0 but stays simple until M1 code exists.

- Native mobile apps — post-MVP, Phase 3 of the product roadmap.

- Read-aloud narration (TTS in Georgian) — post-MVP.

- Physical book printing — post-MVP.

- Multi-developer agent coordination in real time — agents work independently per developer for now.

Zghapari — Built with Claude Code Multi-Agent Pipeline

"არ წაიკითხო ზღაპარი. შექმენი ის ერთად."

"Don't just read a fairy tale. Create it together."